## Dashboard
Event Planning Dashboard
EVENT DETAILS |  | EVENT TEAM
Event Name | [Enter event name] | Event Lead | [Your name]
Event Type | [Conference / Launch / Retreat] | Client Contact | [Name + phone]
Event Date | [YYYY-MM-DD] | Venue Contact | [Name + phone]
Event Time | [Start – End] | A/V Lead | [Name + phone]
Venue | [Location or platform] | Catering | [Name + phone]
Client / Sponsor | [Name] | Emergency Contact | [Name + phone]
BUDGET SUMMARY |  | RSVP BREAKDOWN
Total Budget | 0 | Total Invited | 0
Actual Spend | 0 | Confirmed | 0
Remaining | 0 | Declined | 0
% Used | 0% | Pending | 0
TASK PROGRESS
Tasks Complete | 0 / 33
% Complete | 0%
@erickcabalpro ¦ www.erickcabal.com

## Tasks
Task Checklist
Tasks organized by phase. Status updates feed the dashboard.
Phase | Task | Owner | Due Date | Priority | Status | Notes
3+ Months Out | Define event objectives and success metrics | Event Lead |  | Critical | Not Started
3+ Months Out | Secure budget approval | Finance |  | Critical | Not Started
3+ Months Out | Select and book venue or platform | Event Lead |  | Critical | Not Started
3+ Months Out | Confirm event date and time | Client |  | Critical | Not Started
3+ Months Out | Draft initial guest list | Client |  | High | Not Started
2 Months Out | Book keynote speaker(s) | Event Lead |  | Critical | Not Started
2 Months Out | Contract A/V and production | Event Lead |  | Critical | Not Started
2 Months Out | Confirm catering menu and headcount | Event Lead |  | High | Not Started
2 Months Out | Design invitations and registration page | Designer |  | High | Not Started
2 Months Out | Send save-the-dates | Marketing |  | High | Not Started
1 Month Out | Send formal invitations | Marketing |  | Critical | Not Started
1 Month Out | Begin promotional content | Marketing |  | High | Not Started
1 Month Out | Confirm speaker bios and headshots | Event Lead |  | High | Not Started
1 Month Out | Order signage and printed materials | Designer |  | Medium | Not Started
1 Month Out | Finalize run of show | Event Lead |  | Critical | Not Started
2 Weeks Out | Send reminder to invitees | Marketing |  | High | Not Started
2 Weeks Out | Confirm all vendor arrivals | Event Lead |  | Critical | Not Started
2 Weeks Out | Brief team on roles | Event Lead |  | Critical | Not Started
2 Weeks Out | Do a full tech rehearsal | Event Lead |  | Critical | Not Started
1 Week Out | Send final guest list to venue | Event Lead |  | Critical | Not Started
1 Week Out | Print name tags and materials | Designer |  | High | Not Started
1 Week Out | Confirm transportation and accommodations | Event Lead |  | High | Not Started
Day Before | Set up venue | Event Lead |  | Critical | Not Started
Day Before | Test all tech | A/V Lead |  | Critical | Not Started
Day Before | Prepare welcome packets | Event Lead |  | Medium | Not Started
Event Day | Arrive early for final walk-through | Event Lead |  | Critical | Not Started
Event Day | Manage registration and welcome | Event Lead |  | Critical | Not Started
Event Day | Coordinate run of show live | Event Lead |  | Critical | Not Started
Event Day | Capture photos and key moments | Designer |  | High | Not Started
Post-Event | Send thank-you emails | Marketing |  | High | Not Started
Post-Event | Close out vendor invoices | Finance |  | High | Not Started
Post-Event | Collect attendee feedback | Event Lead |  | High | Not Started
Post-Event | Hold debrief and document learnings | Event Lead |  | Critical | Not Started
Status options: Not Started / In Progress / Blocked / Done
@erickcabalpro ¦ www.erickcabal.com

## Budget
Event Budget
Track estimated vs actual. Variance column auto-calculates.
Category | Item | Vendor | Estimated | Actual | Variance
Venue | Room rental or platform |  | 0 | 0 | 0
Venue | Permits and insurance |  | 0 | 0 | 0
Catering | Food and beverage |  | 0 | 0 | 0
Catering | Service staff |  | 0 | 0 | 0
A/V | Sound system |  | 0 | 0 | 0
A/V | Video production |  | 0 | 0 | 0
A/V | Livestream |  | 0 | 0 | 0
Speakers | Keynote fees |  | 0 | 0 | 0
Speakers | Travel and lodging |  | 0 | 0 | 0
Marketing | Design |  | 0 | 0 | 0
Marketing | Paid promotion |  | 0 | 0 | 0
Printing | Signage |  | 0 | 0 | 0
Printing | Name tags and programs |  | 0 | 0 | 0
Decor | Florals and decor |  | 0 | 0 | 0
Gifts | Attendee gifts |  | 0 | 0 | 0
Gifts | Speaker gifts |  | 0 | 0 | 0
Staff | Event team |  | 0 | 0 | 0
Staff | Security |  | 0 | 0 | 0
Transportation | Shuttle or rideshare |  | 0 | 0 | 0
Misc | Contingency (10%) |  | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0
@erickcabalpro ¦ www.erickcabal.com

## Guests
Guest CRM
Track invitations, RSVPs, and dietary needs.
First Name | Last Name | Email | Company | Role | RSVP | Dietary | Notes
RSVP options: Yes / No / Pending / Waitlist
@erickcabalpro ¦ www.erickcabal.com

## Run of Show
Run of Show
Minute-by-minute timeline. Share with every team lead and vendor.
Time | Duration | Activity | Owner | Notes / Cues
@erickcabalpro ¦ www.erickcabal.com

## Vendors
Vendor Directory
All vendor contracts and contacts in one place.
Category | Vendor | Contact | Phone | Contract $ | Deposit | Status
@erickcabalpro ¦ www.erickcabal.com